## Sheet1
Story ID | Story Name | Iteration | User Story (Description) | Acceptance Criteria | Priority | Story Points | Notes
US-01 | CV Cloud Storage | Sprint 1 | As a TA applicant,I want to save my English CV securely in the cloud,so that I do not need to repeatedly upload the same document for every new application. | 1. Verify that the system allows uploading PDF and Word CVs.2. Verify that users can select their stored CV during a new application process.3. Verify that the stored CV can be updated or deleted. | Must have | 5 | Resolves the redundancy issue where applicants must submit CVs repeatedly.+1
US-02 | Structured Job Posting | Sprint 1 | As a Module Organizer (MO),I want to use structured fields to input workload, hours, and specific tasks when posting a vacancy,so that I can provide complete and clear details to potential TAs. | 1. Verify that the job creation form includes mandatory fields for Course Background, Workload, Hours, and Specific Tasks.2. Verify that the system prevents publishing if any mandatory field is empty. | Must have | 5 | Addresses the lack of core job info (workload, specific tasks) in the current process.+1
US-03 | Detailed Job View | Sprint 1 | As a TA applicant,I want to view the exact workload and specific tasks required on the job page,so that I can accurately judge if the role fits my schedule. | 1. Verify that the job detail page displays all the structured information defined by the MO.2. Verify that the information layout is intuitive and user-friendly. | Must have | 3 | Enables applicants to intuitively assess job matching and workload.
US-04 | QMPlus Integrated Application | Sprint 1 | As a TA applicant,I want to apply using a simple form linked to my QMPlus account,so that I can minimize the effort required to submit my application. | 1. Verify that the system supports Single Sign-On (SSO) via QMPlus credentials.2. Verify that the application interface is a single-page form without complex settings. | Must have | 5 | UI should mimic current questionnaires to minimize learning costs ; integration with QMPlus is recommended.+2
US-05 | Active Status Tracking | Sprint 2 | As a TA applicant,I want to track my application status (e.g., Pending, Screened, Interview, Offer) in a dashboard,so that I am freed from passively waiting for emails. | 1. Verify that a "My Applications" dashboard is available.2. Verify that each application explicitly displays its current processing stage. | Must have | 8 | Shifts from a passive email-waiting model to active tracking.+1
US-06 | Applicant Status Management | Sprint 2 | As a Module Organizer (MO),I want to manually update the hiring stages of applicants in the system,so that students are kept informed of their progress. | 1. Verify that the MO dashboard displays a list of all applicants for their module.2. Verify that changing an applicant's status via the dropdown menu immediately updates the student's view. | Must have | 8 | Necessary backend function for MOs to enable active status tracking for students.
US-07 | Email Notification Tracking | Sprint 2 | As a TA applicant,I want to see whether an MO has sent an official email within the system,so that I can proactively reach out if I missed the notification in my inbox. | 1. Verify that the application detail shows an "Email Sent by MO" status with a timestamp.2. Verify that MO contact details are provided for active follow-up. | Should have | 3 | Creates a closed-loop tracking system for MO emails to prevent missed info.+1
US-08 | Multi-Job Status Differentiation | Sprint 2 | As a TA applicant,I want to see the EBU module code prominently displayed on each application record,so that I can prevent any confusion when managing multiple applications. | 1. Verify that the status tracking list strictly labels each application with its corresponding EBU code and module name. | Should have | 2 | Utilizes EBU course info to clearly separate multiple applications.
US-09 | AI Skill Matching | Sprint 3 | As a system administrator,I want the system to provide an automated skill-matching score based on the CV and job description,so that MOs have a supplementary reference during screening. | 1. Verify that the system calculates a match percentage based on keyword extraction.2. Verify that this matching score is displayed to the MO without blocking manual screening. | Could have | 8 | Users hold reservations about AI accuracy, so this is strictly a supplementary reference.